## Master_List__39
Master Equipment list- Preservation-Unit-39(HC) Date: {DATE}
SR | OPERATING UNIT | Discipline | EQUIP NO | EQUIP DESCRIPTION | Third Party Inspection Status | Pre-Assessment By OEM | Preservation | OEM Name | Remark | Gap Anaysis Remark | Walkdown EM/PF/CPY | G1-Status | G2-Status | G3-Status | G4-Status | Preserved by EU | Preservation | Action By | Expected Dispatch date | Response | Hold Category | N/A Category | Ready For Preservation
Notes:
Note-1: Typical tags are considered for the Electrical and Instrumentation disciplines, as these are standardised items that require a similar preservation philosophy across the plant. Therefore, a common preservation approach has been adopted for these equipment.
Note-2: EnerMech Team confirmation is required on the current preservation status of equipment that has passed L1 inspection and is available for preservation.
Note-3:Equipment currently located at the Vendor’s shop and outside the site is excluded from site preservation activities. Preservation of such equipment shall be managed separately in accordance with the applicable OEM preservation requirements upon completion of repair and testing to site from the respective workshops.
Note-4: No motors for Unit-39 are currently available at site for preservation activities. All HV motors are currently located at the Plenum workshop, while LV motors are undergoing repair and refurbishment at the Adyard workshop. Preservation activities for these motors shall be undertaken upon completion of repair and testing to site from the respective workshops.

## Dashboard
UNIT-39 (HC) PRESERVATION DASHBOARD - DATED:{DATE}
| Activity | Completed | Pending | Hold | N/A / Other | Total | Completion %
Walkdown
G1- Product Drain
G2 - Dew-Point
G3 - O2%
G4 - N2 Blanketing
DISCIPLINE-WISE PRESERVATION STATUS
| Discipline | Total Tags | Walkdown Done | G1 Done | G2 Done | G3 Done | G4 Done | EU -Preserved | Overall Progress
Static
Rotating
Package Mechanical
Piping [4 Circuits]
Category # | Hold Category Description | Tag | Action By | Email Action | EnerMech Recommendation | Note
Total -1
Category # | N/A Category Description | Tag | Action By | Email Action | EnerMech Recommendation | Note
Total -2
Grant Total
Total Equipment Tags(Static and Rotating)
Highlights
Available for Preservation |  |  |  |  | Recommendation: Blind & do N2 blanket to maintain positive pressure.
Piping Circuits |  | 4 | EnerMech | - | 31 lines identified for cleaning among 4 circuits. These lines shall be temporarly kept under nitrogen blanket after cleaning to avoid rapid rusting.
Piping preservation/cleaning strategy:
1. Piping lines will be tracked based on process fluid code under DNV categorized circuits.
2. We recommend not to link piping to its connected equipment as it will create reporting/summarizing issues [Reason: each pipe will connect to at least two or more equipment other than drain/vent lines]
3. EnerMech identified 31 out of 136 lines which needs cleaning. These lines shall be temporarly kept under nitrogen blanket after cleaning to avoid rapid rusting.
| Assets available for preservation | Response

## Proposed Action
Equipment Category | Qty | Reason for Not Preserving / Current Position | Proposed Action
Static & Rotating Equipment | 44 | Limited time for startup. Equipment is currently under inspection/testing, ongoing maintenance/refurbishment, or cleaning, removed from site, or awaiting clearance. Full long-term preservation cannot be completed within the available window before start-up. | Complete all outstanding inspection, cleaning, and maintenance activities. Once equipment is released, to protect the equipment, apply temporary nitrogen blanketing where applicable if a reasonable gap remains before pre-commissioning/start-up. Otherwise, proceed directly to pre-commissioning/commissioning with the required inspection and readiness checks.
Electrical Motors | 55 | Limited time for startup. Motors are new/refurbished and are returning to site from the workshop with applicable test reports. Required electrical tests/checks will also be completed as part of pre-commissioning. With the limited period before start-up, carrying out the same checks again solely to satisfy the preservation cycle would duplicate the pre-commissioning activities. | Review and retain the workshop test reports, complete the applicable pre-commissioning tests/checks, and use these records as evidence of equipment condition/readiness. Do not repeat equivalent tests separately under preservation within the short period before start-up.
E&I Items | 9 | Limited time for startup. Applicable E&I inspection, functional checks and testing are being covered under the pre-commissioning scope. Performing equivalent checks again under preservation immediately before pre-commissioning would result in duplication with limited technical benefit due to the short interval before start-up. | Complete the applicable E&I pre-commissioning inspections/checks/tests and maintain the resulting records as documentary evidence. Avoid repeating equivalent preservation checks/tests where they are already covered by the pre-commissioning scope, subject to Operations approval.
Total | 108

## Categories (hidden)
DASHBOARD CATEGORIES (written by K Data on every export)
• Categories are created and edited in K Data > Dashboard Categories, not in this sheet.
• Code (Cat1, Cat2…) is what the engineer picks in the Hold Category / N/A Category columns of the master list.
• The Dashboard reads this table: one row per category, in this order.
Section | Code | Description | Action By | Email Action | EnerMech Recommendation | Note
Hold | Cat1 | Conflict Between DNV and EnerMech | PF/DNV | Done(16&17, 22 Oct 26) | Preservation Not Requried | Email 26 Oct: Petrofac confirmed these are tube bundles
Hold | Cat2 | Level Transferred to Min Possible | CPY Ops/PF | Done(16 Oct 26) | Only cleaning required, No preservation required | EnerMech: Boil out cleaning proposed to Petrofac
Hold | Cat3 | DNV inspection is ongoing | PF/DNV | Done(16 Oct 26) | Preservation Not Requried
Hold | Cat4 | Under integrity Testing /Hydro Test | CPY Ops/PF | Done(16 Oct 26) | Preservation Not Requried
Hold | Cat5 | Under Installation/work-ongoing | PF | Done(16 Oct 26) | Installation complete, internal work on-going | Installation complete, internal work on-going
N/A | Cat1 | Removed from Site | CPY Ops/PF | Done(16 Oct 26) | Preservation Not Requried
N/A | Cat2 | To be replaced under P5-DBN PJ | Info | Done(16 Oct 26) | Preservation Not Applicable